## 058-A-PID-50001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | A Albalooshi | Please clarify and define safe location.
2 | Cloud+ | 1 | MAK | BMPS-A3
3 | Cloud+ | 1 | MAK | Use the correct no.
4 | Text Box | 1 | A Albalooshi | Orbit Valve is not as per our BMPS-L2 spec for D30N. Please advise the adequacy of this valve.
5 | Cloud+ | 1 | MAK | BMPS-A-50003
6 | Text Box | 1 | David.Jimenez | Equipment basic data?
7 | Cloud+ | 1 | MAK | REFINERY GAS SYSTEM
8 | Text Box | 1 | MAK | Change equipment no. 058Z0001 to 058V5801
9 | Callout | 1 | Francis L | Clarify whether it is a status indicator or alarm.
10 | Cloud+ | 1 | MAK | Delete from all sheets