## 058-A-PID-50002-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Francis L | Provide tag number. Applies to all other similar blocks.
2 | Cloud+ | 1 | MAK | REFINERY GAS SYSTEM
3 | Call-out | 1 | Edgardo | Please indicate the size
4 | Call-out | 1 | Edgardo | Please indicate the tag number for clarity as there are several microscrubber within this unit
5 | Call-out | 1 | Edgardo | Please replace Pig Receiver with Distribution Point (RDP)
6 | Callout | 1 | Francis L | Clarify where comp is performed (ESD or DCS?)
7 | Cloud+ | 1 | MAK | Delete from all sheets
8 | Call-out | 1 | Edgardo | Please confirm the requirement for a valve to be able to isolate the metering package if required
9 | Text Box | 1 | MAK | Change equipment no. 058U0001 to 058U5801