## 058-A-PID-50009-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Edgardo | Revise stream name to "Relief to LSDP Flare"
2 | Callout | 1 | A Albalooshi | Please indicate normally open spectacle blind
3 | Cloud+ | 1 | MAK | Delete
4 | Text Box | 1 | A Albalooshi | Please indicate reducer size
5 | Cloud+ | 1 | MAK | REFINERY GAS SYSTEM
6 | Text Box | 1 | Edgardo | Relief
7 | Call-out | 1 | Edgardo | Change to ball valve
8 | Call-out | 1 | Ali Hasan | Would there be a main 60# steam header to cater for shuting down the secondary header? to be discussed.
9 | Text Box | 1 | Mahdi Ali | THIS APPLICABLE FOR ALL THE PIDS. 1. EQUIPMENT TAG SHALL NOT CONTAIN SPACES. 2. USE UPDATED LINE TYPE FOR FIELDBUS SIGNAL. 3. UNIT ABBREVIATIONS SHALL NOT CONTAIN '#'. ONLY APPROVED ABBREVIATIONS TO BE USED. 4. MAKE SURE THAT CORRECT OPC TYPE IS USED FOR UTILITIES AND PROCESS
10 | Call-out | 1 | Edgardo | Revise stream name to "Relief to Refinery South Flare"
11 | Text Box | 1 | Edgardo | Comment applicable to all sheets: Applicable comments that will be generated and agreed upon during to joint review between ROC and Owner shall also be incorporated in this document
12 | Call-out | 1 | Ali Hasan | Show the line slop
13 | Call-out | 1 | Ali Hasan | Please provide 2" valves with blind (Similar arrangement to the 2” valve at B/L) for steaming out and O2 freeing the flare header/sub-header during flare header commissioning.
14 | Text Box | 1 | Edgardo | Relief
15 | Call-out | 1 | Edgardo | Add the word "Relief" in the stream name