## 058-A-PID-50010-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Ali Hasan | Relief headers to South and LSDP flare is provided for the interconnecting lines. This is to cater for Hub1 T&I during which the South flare will be under shutdown. However, V5817 (Mixing Drum) could also be in operation during Hub1 supplying process gas to some of the BMP units. Would relief from the Mixing drum (RVs, drain, pressure CV) also be connected to South and LSDP flare headers? This item shall be discussed in the P&ID review meeting.
2 | Call-out | 1 | Edgardo | Chage stream name to "Relief to LSDP Flare"
3 | Call-out | 1 | Edgardo | Change stream name to "Relief to Refinery South Flare"
4 | Call-out | 1 | Edgardo | Relief is from RV 1001 in the connecting PID
5 | Cloud+ | 1 | MAK | REFINERY GAS SYSTEM
6 | Cloud+ | 1 | MAK | Delete
7 | Text Box | 1 | Edgardo | Comment applicable to all sheets: Applicable comments that will be generated and agreed upon during to joint review between ROC and Owner shall also be incorporated in this document
8 | Call-out | 1 | Edgardo | Please replace the word "Flare" with "Relief" as highlighted in these stream names
9 | Call-out | 1 | Edgardo | Relief is from RV-1002 in the connecting PID
10 | Call-out | 1 | Edgardo | Change RV1022 with "RV1011", as shown in the connecting PID
11 | Call-out | 1 | Edgardo | Change to "Relief from RV1007/1008, as shown in the connecting PID