## 058-C-DAT-50003-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 2 | A Albalooshi | Include demister material
2 | Callout | 2 | A Albalooshi | SA 516 GR 70N
3 | Callout | 3 | A Albalooshi | Include in removable items
4 | Callout | 4 | A Albalooshi | 2" inlet nozzle for 60 pound steam is not represented as per P&ID
5 | Callout | 4 | A Albalooshi | 2" Nozzle is not represented as per P&ID
6 | Callout | 4 | A Albalooshi | 6" nozzle is not represented as per P&ID
7 | Callout | 5 | A Albalooshi | Line sizes in the P&IDs are preliminary and this shall be finalized along with Hydraulic calculations during detailed engineering stage of the EPC “The sizes are minimum in the P&IDs”. This document shall be updated after unfreezing the “HOLD” from the P&IDs.