## 061-A-BOD-50002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | General Comment: Use the latest document template that is part of the Homogenisation Procedure.
2 | Call-out | 1 | Edgardo | Please change to WHARF
3 | Text Box | 8 | Edgardo | #53
4 | Text Box | 8 | Edgardo | #54
5 | Call-out | 8 | Edgardo | Please indicate the assigned Sealine number for the C3/C4 liquid line and vapor return line
6 | Typewritten Text | 8 | Nabeel | we need to add #10 Sealine for kerosene service
7 | Typewritten Text | 12 | Nabeel | #50
8 | Call-out | 12 | Edgardo | Please refer to comment on elastomer in Page 15
9 | Call-out | 13 | Edgardo | Please change this sign with the word "to"
10 | Call-out | 13 | Ahmed Bucheeri | To re-confirm this statement for the crude importing at low points of the line especially the sub sea sections.
11 | Call-out | 14 | Mahdi Ali | Change to '061'
12 | Typewritten Text | 14 | Nabeel | mention the sea line numbers #53 and #54
13 | Call-out | 14 | Edgardo | Please change to "Return" for consistency with the text shown in page 8 of this document
14 | Call-out | 14 | Ahmed Bucheeri | What about CA against CUI. To clairfy.
15 | Call-out | 15 | Edgardo | Please clarify the word "elastomers". It is suggested to consider using the word "Gaskets" as this seems to be a more general and appropriate word; the required gasket for MTBE service is already defined in Pipe Spec B50 included in BMPS-L2
16 | Call-out | 16 | Ahmed Bucheeri | All new sea lines including C3 and C4 and existing No.19 sea line
17 | Call-out | 16 | Ahmed Bucheeri | An item to be added for external lining for C3 and C4 lines including associated vessels and valves for protection against CUI.
18 | Call-out | 16 | Mahdi Ali | Remove space between tag and suffix
19 | Call-out | 17 | Jawad Alawi | New sea lines will be of bare type and CWC pipes will not be an option