## 061-A-PID-00004-002-R5A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | BAPCO LEGACY DRAWING NO. BRA080071 SHEET 2
2 | Call-out | 1 | Edgardo | Please change this drawing number to 061-A-PID-00015-001
3 | Callout | 1 | Abdul Rahim | Kero/JP5 flushing
4 | Text Box | 1 | Mahdi Ali | ADD THE ABOVE NOTE BELOW THE DRAWING NUMBER AS WAS ORIGINALLY PROVIDED BY BAPCO. DO NOT REMOVE THIS NOTE FROM ALL THE PID PROVIDED BY BAPCO.
5 | Call-out | 1 | Edgardo | Please clarify why this line has two line numbers
6 | Callout | 1 | Francis L | Clarify whether this tag is to be decommissioned.
7 | Callout | 1 | Abdul Rahim | /JP5
8 | Call-out | 1 | Mahdi Ali | RETAIN EXISTING INFORMATION. THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINAL HANDOVER. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS
9 | Call-out | 1 | Edgardo | Please clarify why this line has two line numbers
10 | Call-out | 1 | Edgardo | Please delete this legend
11 | Call-out | 1 | Edgardo | Please delete this mark-up on the line