## 061-A-PID-00005-001-R5A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Edgardo | These lines are assigned two line numbers each
2 | Call-out | 1 | Edgardo | Please delete this legend
3 | Pen | 1 | Edgardo | To
4 | Pen | 1 | Edgardo | or
5 | Callout | 1 | Abdul Rahim | place Berth 2 & 4 for all line or on the left hand side of all sealines.
6 | Pen | 1 | Edgardo | on
7 | Text Box | 1 | Mahdi Ali | BAPCO LEGACY DRAWING NO. BRA080073 SHEET 1
8 | Call-out | 1 | Edgardo | Please delete the shade at this portion to show that this is not part of the decommissioned line
9 | Pen | 1 | Edgardo | {
10 | Call-out | 1 | Edgardo | Please delete the mark-up on these lines with MTBE
11 | Callout | 1 | Abdul Rahim | place Berth 2 & 4 for all line or on the right hand side of all sealines.
12 | Call-out | 1 | Edgardo | Please provide flange connection at minimum distance from the tie-in point to allow for the isolation / blinding of the decommissioned portion of line
13 | Pen | 1 | Edgardo | to
14 | Call-out | 1 | Edgardo | Please relocate location of tie-in for S/L 13 downstream of the 1 1/2" stub
15 | Call-out | 1 | Edgardo | These lines are provided with two line numbers each
16 | Text Box | 1 | Mahdi Ali | ADD THE ABOVE NOTE BELOW THE DRAWING NUMBER AS WAS ORIGINALLY PROVIDED BY BAPCO. DO NOT REMOVE THIS NOTE FROM ALL THE PID PROVIDED BY BAPCO.
17 | Cloud | 1 | Mahdi Ali
18 | Call-out | 1 | Edgardo | Please indicate the stream name of this line
19 | Call-out | 1 | Edgardo | Please relocate this tie-in at downstream of the 4" stub
20 | Call-out | 1 | Edgardo | Please relocate this tie-in downstream of the 1 1/2" stub
21 | Call-out | 1 | Mahdi Ali | RETAIN EXISTING INFORMATION. THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINAL HANDOVER. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS
22 | Pen | 1 | Edgardo | s
23 | Pen | 1 | Edgardo | s
24 | Call-out | 1 | Edgardo | Please clarify if these instrumentation will be decommissioned also