## 061-A-PID-00005-003-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | BAPCO LEGACY DRAWING NO. BRA080073 SHEET 3
2 | Call-out | 1 | Mahdi Ali | RETAIN EXISTING INFORMATION. THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINAL HANDOVER. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS
3 | Call-out | 1 | Edgardo | Its is suggested to change the drawing title to 'T' Head Interconnecting Lines to Berth 1 and 3
4 | Text Box | 1 | Mahdi Ali | ADD THE ABOVE NOTE BELOW THE DRAWING NUMBER AS WAS ORIGINALLY PROVIDED BY BAPCO. DO NOT REMOVE THIS NOTE FROM ALL THE PID PROVIDED BY BAPCO.
5 | Call-out | 1 | Edgardo | For better clarity of the PID presentation, it is suggested to relocate these Berth 2 piping to a separate sheet, to be titled T Head Interconnecting Lines to Berth 2 and 4