## 061-A-PID-00006-002-R4A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Abdul Rahim | for better presentation change the location of 19 S/L on this sheet
2 | Call-out | 1 | Mahdi Ali | RETAIN EXISTING INFORMATION. THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINAL HANDOVER. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS
3 | Text Box | 1 | Mahdi Ali | BAPCO LEGACY DRAWING NO. BRA080074 SHEET 2
4 | Call-out | 1 | Edgardo | Please provide 1 1/2" stub with valve and plug at downstream of these isolating valves to allow for hose connection during flushing of lines
5 | Text Box | 1 | Mahdi Ali | ADD THE ABOVE NOTE BELOW THE DRAWING NUMBER AS WAS ORIGINALLY PROVIDED BY BAPCO. DO NOT REMOVE THIS NOTE FROM ALL THE PID PROVIDED BY BAPCO.