## 061-A-PID-00007-001-R5A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | ADD THE ABOVE NOTE BELOW THE DRAWING NUMBER AS WAS ORIGINALLY PROVIDED BY BAPCO. DO NOT REMOVE THIS NOTE FROM ALL THE PID PROVIDED BY BAPCO.
2 | Callout | 1 | Abdul Rahim | /JP5 flushing
4 | Call-out | 1 | Edgardo | This portion of S/L No. 5 to Berth 2 will be decommissioned
5 | Call-out | 1 | Mahdi Ali | RETAIN EXISTING INFORMATION. THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINAL HANDOVER. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS
6 | Callout | 1 | Abdul Rahim | explain Fuel oil which se
7 | Call-out | 1 | Edgardo | These lines are assigned two line numbers
8 | Text Box | 1 | Mahdi Ali | BAPCO LEGACY DRAWING NO. BRA080076 SHEET 1
9 | Call-out | 1 | Edgardo | These lines are assigned two line numbers each
10 | Call-out | 1 | Edgardo | Please provide a 1 1/2" stub downstream of the isolating valve to allow for hose connection during flushing of the line
11 | Call-out | 1 | Edgardo | Please delete this legend
12 | Call-out | 1 | Edgardo | Please delete this markup on the lines
13 | Call-out | 1 | Edgardo | Please change this drawing number to 061-A-PID-50005-001