## 061-A-PID-00007-002-R4A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Francis L | Clarify the need for this PG to be excluded from demolition.
2 | Call-out | 1 | Edgardo | This proposed connection of S/L # 5 replacement line to Wharf No. 1 shall be relocated to 061-A-PID-00004-001
3 | Call-out | 1 | Edgardo | This portion of S/L No. 5 to Berth No. 2 will be decommissioned
4 | Call-out | 1 | Mahdi Ali | RETAIN EXISTING INFORMATION. THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINAL HANDOVER. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS
5 | Text Box | 1 | Mahdi Ali | ADD THE ABOVE NOTE BELOW THE DRAWING NUMBER AS WAS ORIGINALLY PROVIDED BY BAPCO. DO NOT REMOVE THIS NOTE FROM ALL THE PID PROVIDED BY BAPCO.
6 | Text Box | 1 | Mahdi Ali | BAPCO LEGACY DRAWING NO. BRA080076 SHEET 2