## 061-A-PID-00008-001-R4A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Pen | 1 | Edgardo | w
2 | Pen | 1 | Edgardo | +
3 | Pen | 1 | Edgardo | no
4 | Pen | 1 | Edgardo | .
5 | Pen | 1 | Edgardo | .
6 | Call-out | 1 | Edgardo | Please consider relocating the tie-ins on these lines downstream of the flange connections, to be able to isolate / blind the main line during installation of tie-ins
7 | Pen | 1 | Edgardo | .
8 | Text Box | 1 | Mahdi Ali | BAPCO LEGACY DRAWING NO. BRA080078 SHEET 1
9 | Pen | 1 | Edgardo | ^
10 | Call-out | 1 | Mahdi Ali | RETAIN EXISTING INFORMATION. THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINAL HANDOVER. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS
11 | Call-out | 1 | Edgardo | These will also be decommissioned
12 | Text Box | 1 | Mahdi Ali | ADD THE ABOVE NOTE BELOW THE DRAWING NUMBER AS WAS ORIGINALLY PROVIDED BY BAPCO. DO NOT REMOVE THIS NOTE FROM ALL THE PID PROVIDED BY BAPCO.
13 | Call-out | 1 | Edgardo | This portion of Sealine No. 19 may need to be retained, since the chamber for pigging is at the end if this line shown in 061-A-PID-00008-002
14 | Pen | 1 | Edgardo | .
15 | Pen | 1 | Edgardo | /
16 | Pen | 1 | Edgardo | m
17 | Pen | 1 | Edgardo | ^
18 | Pen | 1 | Edgardo | .
19 | Pen | 1 | Edgardo | `
20 | Pen | 1 | Edgardo | m
21 | Pen | 1 | Edgardo | .
22 | Pen | 1 | Edgardo | in