## 061-A-PID-50016-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | Page 1 | Francis L | Provide a Note or signal connection to show the conditions for pump operation. Applies to other similar/ and relevant tags.
2 | Callout | Page 1 | Francis L | Sequential numbers of tags associated with ESD shall be of 8000 series. Applies to all other similar tags.
3 | Callout | Page 1 | Abdul Rahim | Confirm if one or two pumps. check basis of design
4 | Callout | Page 1 | Abdul Rahim | explain this will overflow in no time. discuss.
5 | Callout | Page 1 | Abdul Rahim | discuss the need to automate this
6 | Text Box | Page 1 | MAK | 061M6111A
7 | Text Box | Page 1 | MAK | General Comment to be applied to all P&IDs: As per BMPS-A8, Section 8.4.3, Drivers Tag Nos. e.g. Motors/Turbines shall always be inserted in all P&IDs and placed below the parent equipment no. e.g. Pump/Fan/Mixer/Cooler where possible. Motor FinFan tag nos. shall always be shown where applicable.