## 061-C-DAT-50001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 4 | A Albalooshi | Update vent location based on the P&ID stream location/ sequence. Otherwise update the P&ID
2 | Callout | 5 | A Albalooshi | Line sizes in the P&IDs are preliminary and this shall be finalized along with Hydraulic calculations during detailed engineering stage of the EPC “The sizes are minimum in the P&IDs”. This document shall be updated after unfreezing the “HOLD” from the P&IDs.