## 061-C-GAD-50001-003-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Ahmed Bucheeri | 061V6120A/B
2 | Call-out | 1 | Ahmed Bucheeri | A/B
3 | Call-out | 1 | Edgardo | It is noted in PID that these are to be provided with 90 deg elbows at ends; please clarify
4 | Callout | 1 | A Albalooshi | Nozzle location/ sequence shall be consistence either update in GA or data sheet reference document BMP-ROC-TRI-00366
5 | Call-out | 1 | Edgardo | Please clarify if this is davit or hinge for the manway cover; refer to BMPS std dwg GF-C87280
6 | Call-out | 1 | Edgardo | Please clarify the location of this nozzle; this is the temperature gauge
7 | Callout | 1 | Chandrahasan D | Show load values in metric units within brackets (Kg or KN)