## 061-C-GAD-50002-003-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Edgardo | Athough this dimensiojn is shown as HOLD, the height of this vessel will need to be confirmed; please clarify if lugs for the platform are to be provided
2 | Call-out | 1 | Edgardo | Please clarify the provision of insulation support rings; this vessel will be insulated
3 | Call-out | 1 | Edgardo | Please clarify whether this is a hinge or davit; refer to BMPS std dwg GF-C87280
4 | Callout | 1 | Chandrahasan D | Show load values in metric units within brackets (Kg or KN)