## 061-G-DAT-50001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Callout | 2 | Abdul Rahim | this diesel slop can be heaver
3 | Text Box | 2 | Sankara | Add: Gas Group IIB
4 | Cloud+ | 2 | MAK | 061 - SITRA WHARF
5 | Callout | 5 | A Albalooshi | Required
6 | Callout | 5 | A Albalooshi | Radiography is required
7 | Call-out | 6 | Edgardo | Please change to "depth"
8 | Callout | 8 | Abdul Rahim | this is very low, the slop from fuel has heavier viscosity. fuel viscosity380 cst. therefore if it is cut with little diesel then the vosocity could be > 200cst
9 | Callout | 8 | Mahdi Ali | INCORRECT TAG NUMBERS. TAG NUMBERS SHALL INCLUDE UNIT NUMBER