## 061-S-DAT-50003-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 3 | Omran A | General Comment: and accordingly field equipment, panels to be selected.
2 | Text Box | Page 1 | Edgardo | General Comment: The comments in this document apply to all black product loading arms at Wharf Nos. 1 & 2
3 | Callout | Page 2 | Abdul Rahim | why not 22000 BPH
4 | Callout | Page 2 | Abdul Rahim | is this equvelent to 380 Sct. Bapco fuel oil spec.
5 | Callout | Page 2 | Abdul Rahim | refer to all comments on 061LA6112 berth #1 white product loading arm.
6 | Callout | Page 2 | A Albalooshi | Please confirm the size
7 | Callout | Page 2 | Chandrahasan D | <add> Design Basic wind speed for operating and idle conditions
8 | Callout | Page 3 | Abdul Rahim | import
9 | Call-out | Page 3 | Mohamed Aldoseri | Refer to comments in (061-S-DAT-50002-001)
10 | Callout | Page 3 | A Albalooshi | Along with pressure gauge.
11 | Call-out | Page 3 | Edgardo | Wireless is not acceptable; Refer to Clause 10.1.4 of BMPS-M5
12 | Call-out | Page 3 | Edgardo | As per Queries No. T679 and T887, each loading arm shall be able to be separately and independently controlled with adequate segregation between each loading arm control systems, for ease of maintenance
13 | Callout | Page 3 | Chandrahasan D | <add> Minimum vessel size in addition to the maximum vessel size
14 | Call-out | Page 4 | Edgardo | For consistency and clarity, please indicate the assigned loading arm number
15 | Text Box | Page 4 | Chandrahasan D | General: The minimum value of M in the existing wharf operations is 3m The value B in existing T wharf is more than 6m This spacing J need to be checked with pile row spacing to avoid interference with existing structures The O range value is very narrow and needs to be checked with vessel size range
16 | Callout | Page 4 | Chandrahasan D | counterweight movement envelope to be provided by vendor and EPC contractor to check and ensure that no interference with existing structure/services and personnel movement
17 | Text Box | Page 4 | Chandrahasan D | General: Missing Dimensions F,G,H &I to be provided by vendor and to be verified by EPC contractor?? Vendor to provide Loading information for design of Structures/foundation