## 061-S-DAT-50004-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 1 | Edgardo | General comment: The comments in this document applies to all documents related to the propane / butain service
2 | Callout | Page 2 | Chandrahasan D | <add> Design Basic wind speed for operating and idle conditions
3 | Callout | Page 3 | Abdul Rahim | To be investigated by Technip not Bapco
4 | Callout | Page 3 | Abdul Rahim | Banagas loading arm can achieve as low as 50 metric ton per hour
5 | Callout | Page 3 | Abdul Rahim | refer to 061LA 6112 comments
6 | Call-out | Page 3 | Mohamed Aldoseri | Refer to comments in (061-S-DAT-50002-001)
7 | Call-out | Page 3 | Edgardo | As per Queries No. T679 and T887, each loading arm shall be able to be separately and independently controlled with adequate segregation between each loading arm control systems, for ease of maintenance
8 | Call-out | Page 3 | Edgardo | Wireless is not acceptable; Refer to Clause 10.1.4 of BMPS-M5
9 | Callout | Page 3 | Chandrahasan D | <add> Minimum vessel size in addition to the maximum vessel size
10 | Call-out | Page 4 | Edgardo | For consistency and clarity, please indicate the assigned loading arm number
11 | Text Box | Page 4 | Chandrahasan D | General: The minimum value of M in the existing wharf operations is 3m The value B in existing T wharf is more than 6m This spacing J need to be checked with pile row spacing to avoid interference with existing structures The O range value is very narrow and needs to be checked with vessel size range
12 | Callout | Page 4 | Chandrahasan D | counterweight movement envelope to be provided by vendor and EPC contractor to check and ensure that no interference with existing structure/services and personnel movement
13 | Text Box | Page 4 | Chandrahasan D | General: Missing Dimensions F,G,H &I to be provided by vendor and to be verified by EPC contractor?? Vendor to provide Loading information for design of Structures/foundation