## 079-A-BOD-00002-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | Equipment List for Unit 079 shall be submitted to Bapco for review.
2 | Callout | 7 | Mahdi Ali | 1&2SGP
3 | Callout | 7 | Mahdi Ali | AVOID USING THE WORD 'NEW'. THIS APPLIES TO THE ENTIRE DOCUMENT
4 | Cloud+ | 10 | MAK | Tag nos. shall not contain spaces.
5 | Call-out | 10 | Edgardo | Please clarify and confirm the routing of the KMU spent caustic to the Spent Caustic Treating Plant
6 | Callout | 10 | Mahdi Ali | 1&2SGP
7 | Callout | 10 | Mahdi Ali | UNIT NUMBERS SHALL NOT BE PREFIXED WITH AREA CODE
8 | Cloud+ | 11 | MAK | Tag nos. shall not contain spaces.
9 | Call-out | 11 | Ahmed Bucheeri | Internal coating to be specified for the closed drain drum 79V0001
10 | Call-out | 12 | Ahmed Bucheeri | To add the closed drain drum 79V0001
11 | Cloud+ | 12 | MAK | 079D0001