## 079-A-PFD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | [1] Model | Mahdi Ali | Change to 386-A-PFD-00001-007
2 | Text Box | [1] Model | MAK | Equipment List of this Unit shall be provided to the Bapco for review.
3 | Call-out | [1] Model | Edgardo | Please indicate the unit numbers in the B/L
4 |  | [1] Model | AutoCAD SHX Text | The present document or drawing is property of TECHNIP ITALY S.p.A. and shall not, under any circumstances, be totally or partially, directly or indirectly, transferred, reproduced, copied, disclosed or used, without its prior written consent, for any purpose and in any way other than that for which it is specifically furnished or outside the extent of the agreed upon right of use.
5 | Call-out | [1] Model | Edgardo | For the required information on pump capacity and differential head, please refer to data sheet BRE-201369 which was attached to Query T1161
6 | Line | [1] Model | MAK
7 | Call-out | [1] Model | MAK | Change to 386-A-PFD-00001-003
8 | Callout | [1] Model | Salman Jaffer | Discrepancy between this document and the FEED Process Design Basis Clause 9 table 8.1 for pressure of stream #1has to be resloved. In PDB the pressure is 30 psig and in this document and SGP PFD is 25 psig.
9 | Call-out | [1] Model | MAK | T
10 | Call-out | [1] Model | MAK | Change to 386-A-PFD-00001-003
11 | Call-out | [1] Model | Edgardo | Please indicate the document number of the connecting PFD document
12 | Call-out | [1] Model | MAK | Change to 386-A-PFD-00001-003
13 | Call-out | [1] Model | Hasan Al Noaimi | It should be vented to a safe place not atmossphere.