## 079-A-PID-00002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Ali Hasan | •The spent caustic pumps shall be provided with bound wall and appropriate drainage facilities to contain any caustic spills during pumps maintenance. Please show the bound wall and drainage in the P&ID. •The bound wall area to be caustic resistance. •Please refer to the Note related to the chemical packages in 1RHCU and 3HDU for consistency between the packages e.g. Note 2 in P&ID 021-A-PID-00062-001.
2 | Text Box | 1 | MAK | 079M0002A
3 | Text Box | 1 | MAK | 079M0002B
4 | Call-out | 1 | Ali Hasan | Add a UC (utility connection) for the pump washing during maintenance. A note to be added to indicate the need to install a utility station (FED water) near the UC. Refer to our comment on P&ID 079-PID-00001-001 about the UC.
5 | Callout | 1 | Francis L | Add associated tag ie. SIGNAL FROM SEQ BLOCK OF LC-0003
6 | Call-out | 1 | Ali Hasan | Add PG in the suction line of each pump
7 | Call-out | 1 | Ali Hasan | Caustic drains will be routed to closed drain (079V0001). However, drain connection with ‘R’ is applicable to oil drains (RPSO-Recovery Process Slop Oil). New abbreviation/suffix to be created for the caustic closed drain and added to the Misc. connections in Sheet 2 of the BMPS-A-50003. This is a general item applies to all the drains in caustic service.
8 | Callout | 1 | Francis L | Check spacing
9 | Call-out | 1 | Ali Hasan | Drain valve to be connected to the open and closed drains connection provided on the pump suction line. Please refer to pump 023P0001A/B (1HRU P&ID 023-A-PID-00001-001) for reference.
10 | Group | 1 | MAK | General Comment to be applied to all P&IDs: As per BMPS-A8, Section 8.4.3, Drivers Tag Nos. e.g. Motors/Turbines shall always be inserted in all P&IDs and placed below the parent equipment no. e.g. Pump/Fan/Mixer/Cooler where possible. Motor FinFan tag nos. shall always be shown where applicable.
11 | Callout | 1 | Francis L | Indicate as LI-0002
12 | Callout | 1 | Francis L | Indicate SP for this signal, here.
13 | Callout | 1 | Francis L | Is there a requirement for this indicator to be readable from the bypass valve of FV-0001? If so, insert a note.
14 | Call-out | 1 | Ali Hasan | PFD 079-A-PFD-0001-001 show the spent caustic from 079D0001 is directly connected to 079U0001 without going through 079P0002A/B. PFD to be updated if 079P0002A/B arrangement in the P&ID is correct.
15 | Call-out | 1 | Ranjit | Please clarify the purpose of this untreated spent caustic line to WWTP. WHen is it expected to be used.
16 | Callout | 1 | A Albalooshi | Please indicate size
17 | Callout | 1 | A Albalooshi | Please indicate strainer size
18 | Callout | 1 | A Albalooshi | Please indicate the reducer size
19 | Callout | 1 | A Albalooshi | Please indicate the size
20 | Callout | 1 | A Albalooshi | Please indicate the size
21 | Callout | 1 | A Albalooshi | Please indicate the size
22 | Callout | 1 | A Albalooshi | Please indicate the size
23 | Callout | 1 | A Albalooshi | Please indicate the size
24 | Call-out | 1 | Ranjit | Provide DCS TI on the suction line
25 | Call-out | 1 | Ali Hasan | Show drain valve at the lowest point of the strainer.
26 | Call-out | 1 | Ali Hasan | The spent caustic can be fouling service due to contamination from 1&2SGP or KMU. Local differential pressure gauge (PDG) across the Y-strainer to be provided for each pump.
27 | Call-out | 1 | Ranjit | This valve to be globe type to control the flow
28 | Call-out | 1 | Ali Hasan | Use plug instead of blind (boiler maker). Plug on drain valve is preferred over blind for ease of removal unless the piping class or the drain size dictate. This is general comment