## 079-A-PID-00006-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mahdi Ali | 015D0269
2 | Call-out | 1 | Ranjit | Complete the description
3 | Call-out | 1 | Ali Hasan | FC0002 is provided on the spent caustic line to V0002. FI0004 is redundant and to be deleted. TI 0005 can be located near FC0002 for compensation.
4 | Call-out | 1 | Ranjit | In this P&ID, the fresh and spent caustic connection also has a connection to the OWS. Please review and confirm that these streams can be routed to the OWS without any corrosion issues. The implication of routing this to OWS and potential recirculation through Slops also needs to be reviewed.
5 | Callout | 1 | A Albalooshi | Please indicate the size
6 | Call-out | 1 | Ranjit | Provide a specatcle bling here.
7 | Call-out | 1 | Ranjit | Provide check valve
8 | Call-out | 1 | Ranjit | Provide check valve
9 | Call-out | 1 | Ranjit | Provide check valve