## 079-C-GAD-00002-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | Fill in EX and PN nos.
2 | Text Box | 1 | MAK | Equipment List for Unit 079 was not issued for Owner review.
3 | Cloud+ | 1 | MAK | 079 - SPENT CAUSTIC TREATING UNIT
4 | Call-out | 1 | Ahmed Bucheeri | Full RT due to PWHT
5 | Text Box | 1 | MAK | General Comment: All the texts in drawings shall be searchable and in UPPERCASE. Text fonts and styles shall be as per BMPS-A8.
6 | Callout | 1 | A Albalooshi | Revised size as per P&ID mark up review to 4"
7 | Call-out | 1 | Ahmed Bucheeri | Internal coating is required against internal corrosion, coating system to be selected basis the service contents and design temperature
8 | Cloud+ | 1 | MAK | 3