## 079-G-DAT-00001-001-RB
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Call-out | 2 | Ali Hasan | Refer to comment on page 7
3 | Callout | 2 | Mahdi Ali | 079 - SPENT CAUSTIC TREATING UNIT
4 | Text Box | 2 | A Albalooshi | The information provided for the driver starting method of the pumps is not applicable (Closed/Open – valve (unloaded) start)), It shall be corrected as DOL or VFD starting method as per detail design. Please provide the basis/ philosophy of providing this requirement on the driver starting method. A general note shall be added as follows "Motors shall be designed to suite the driver online starting method as per BMPS-P19 clause 5.4 and BMPS-P18 clause 5.4.". The (Closed/Open – valve (unloaded) start)) shall be moved in the relevant field in the data sheet.
5 | Call-out | 2 | Ali Hasan | With reference to SCTU PFD 079-PFD-00001-001 Note 2, please add the following: Pump capacity is preliminary. To be finalized according to closed drain final size.
6 | Call-out | 3 | Ali Hasan | Please refer to the comment on page 7 about the design temperture
7 | Text Box | 4 | AliRedha Malalla | M/Seal plan to be changed; it shall handle toxic and high H2S service. Please ensure with Pump and Seal manufacturers on the proposed selection for an INTERMITTENT service.
8 | Text Box | 7 | Ali Hasan | Please review the design temperature. Spent or treated caustic drains from 079U0001 (Spent Caustic Package) will also be routed to 079V0001 and then pumped by 079P0001A/B. The temperature of these drain is hot exceeding the discharge piping temperature of 165 degF. Hence, the design temperature shall be corrected to cater for hot draining.
9 | Call-out | 8 | Hasan Al Noaimi | full set pump and motor should be in the Warehouse
10 | Call-out | 8 | Ali Hasan | This pump handle caustic with high concentration of H2S. The caustic is also a toxic fluid. Please modify the pump service.