## 079-G-DAT-00002-001-RC
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | General Comment: This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template and cover page shall be used.
2 | Callout | 1 | A Albalooshi | Refer to BMP-ROC-TRI-00394, the same tag number was found. Please clarify.
3 | Call-out | 1 | MAK | Delete space
4 | Call-out | 2 | Mohamed Aldoseri | Data shall be confirmed after approving the hazardous area classification drawing
5 | Text Box | 2 | Mohamed Aldoseri | X
6 | Call-out | 2 | Mohamed Aldoseri | Wrong data, provide the correct information
7 | Cloud+ | 2 | MAK | 079 - SPENT CAUSTIC TREATING UNIT
8 | Call-out | 4 | Ali Hasan | Please confirm the seal type considering the pumping fluid is high H2S and toxic service.
9 | Call-out | 7 | Ali Hasan | This is H2S service pump with very high H2S concentration. Please modify to H2S and toxic service. Please include the H2S normal/max concentration in the process data sheet.