## 081-A-STS-50001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mahdi Ali | THIS DOCUMENT IS A CALCULATION SHEET AND NOT A STUDY. THUS THE DOCUMENT TYPE SHALL BE 'CAL' AND NOT 'STS'. CHANGE ALL THE REFERENCES TO THIS DOCUMENT ACCORDIGNLY. HOWEVER, IF THIS DOCUMENT IS A STUDY THEN THE TITLE SHOULD BE CHANGED ACCORDINGLY.
2 | Text Box | 1 | MAK | Bapco has not received the Unit Equipment List (Item Index) for review. How to cross check the correctness/completeness of equipment numbers within this document?? Equipment List is the master index and shall be issued before issuing this document.
3 | Text Box | 2 | MAK | General Comment: Equipment List for Unit 081 was not issued for review. However, this list shall perfectly match Unit 081 - Equipment List (Item Index). All Units equipment shall be included for Criticality Rating Evaluation.
4 | Typewritten Text | 2 | steven.coyne | Add reference to Criticality Procedure : 000-A-PRO-50017-001
5 | Call-out | 2 | MAK | Add missing pump drivers: 081M8102A 081M8102B
6 | Cloud+ | 2 | MAK | Delete space
7 | Text Box | 2 | A Albalooshi | Please relate the criticality ratings with the inspection levels.