## 082-A-PPN-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Set in Roman | 1 | David.Jimenez | Set in Roman
2 | Set in Roman | 1 | David.Jimenez | Set in Roman
3 | Set in Roman | 1 | David.Jimenez | Set in Roman
4 | Set in Roman | 1 | David.Jimenez | Set in Roman
5 | Callout | 1 | Robert.Kawitzki | Indicate tip of flare EL
6 | Callout | 1 | A Albalooshi | Contractor to consider minimum width of walk way, stairs and pedestrain footpaths as 1.2 meters.
7 | Text Box | 1 | Robert.Kawitzki | Move to planview
8 | Callout | 1 | Robert.Kawitzki | Pipe rack missing in this section
9 | Set in Roman | 1 | David.Jimenez | Set in Roman
10 | Text Box | 1 | Chandrahasan D | List of Equipments??. If shown in a separate drawing, it shall be shown in reference drawings
11 | Callout | 1 | Robert.Kawitzki | Show EL
12 | Callout | 1 | Chandrahasan D | Battery Limit and Continuation line are same??
13 | Callout | 1 | Chandrahasan D | Verify the legend items and only include the items relevant to this drawing OR Prepare a common Legend and abbreviation drawing for use of all Operating centers and include it a reference drawing here.
14 | Callout | 1 | Robert.Kawitzki | I am assuming the flare line comes from the pipe rack? If so, then the pipe is shown going the wrong way. Is there enough room to make a double bend?
15 | Callout | 1 | Mahdi Ali | INCORRECT UNIT DESCRIPTION
16 | Callout | 1 | Robert.Kawitzki | How can the flare line be lower than the knockout vessel before entry? This cannot be right
17 | Callout | 1 | Chandrahasan D | <revise after corresponding to > UTM ZONE 39 COORDINATES â€“ AIN AL ABD DATUM <before N=288..>
18 | Callout | 1 | Chandrahasan D | <add in front of Local> REFINERY
19 | Cloud+ | 1 | MAK | Change to: 082 - REFINERY SOUTH FLARE
20 | Callout | 1 | Chandrahasan D | Include Reference drawings
21 | Callout | 1 | Robert.Kawitzki | Locate text in a readable position
22 | Text Box | 1 | Robert.Kawitzki | Column markers to be shown and string dimensioned - typical comment
23 | Callout | 1 | Robert.Kawitzki | Show TOS - typ comment
24 | Callout | 1 | Robert.Kawitzki | Show easting and northings for all matchlines - typical comment
25 | Cloud | 1 | Mahdi Ali
26 | Cloud+ | 1 | MAK | Fill in E.X. and P.N. nos.
27 | Callout | 1 | Robert.Kawitzki | Leave a minimum of 1000mm paving around extremities of equipment
28 | Callout | 1 | Robert.Kawitzki | Move the E to the coordinate
29 | Cloud+ | 1 | MAK | Change to: 082 - REFINERY SOUTH FLARE
30 | Text Box | 1 | Mahdi Ali | UNIT 000 SHALL NOT BE USED. ALL INTERCONNECTING AREAS HAVE A DEDICATED UNIT NUMBERS.
31 | Callout | 1 | Robert.Kawitzki | All dimensions shall be shown on plan view. ELs on sections only - typical comment
32 | Callout | 1 | Mahdi Ali | ANY MODIFICATIONS TO UNIT 080 (LSDP FLARE) SHALL BE MADE ON THE DEDICATED UNIT PLOT PLAN FOR THE LSDP FLARE ITSELF. PLOT PLANS OF TWO DIFFERENT UNITS SHALL NOT BE COMBINED. BAPCO HAS A PLOT PLAN FOR UNTI 081.
33 | Callout | 1 | Mahdi Ali | CONTINUATION TO WHERE?
34 | Callout | 1 | Chandrahasan D | <show> Width of corridor
35 | Callout | 1 | Robert.Kawitzki | Show EL TOS
36 | Call-out | 1 | Edgardo | Comments: 1. The drawing title is not consistent with the contents of the drawing. The title is about the general plot plan; however, the contents of the drawing include both the plot plan, elevations and sections. 2. This drawing is for Unit 082. However, the contents of the drawing includes also the plot plan for Unit 081. the latter should be on a separate drawing number. If it is realy necessary to show the layout of Unit 081, it should only be shown in dash lines and not as a plot plan, where the new equipment are shown in solid lines