## 082-C-DAT-00002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | A Albalooshi | Equipment tag number is not represented in any P&ID. Please clarify this tag.
2 | Call-out | 2 | Ahmed Bucheeri | Full radiograph is required due to PWHT
3 | Callout | 2 | A Albalooshi | No relevant note.
4 | Callout | 2 | A Albalooshi | Required
5 | Call-out | 2 | Ahmed Bucheeri | To confirm the material and the spec/grade
6 | Call-out | 3 | Ahmed Bucheeri | To confirm the selection of the 304SS cladding, since feed MSD does not show metallic internal lining
7 | Callout | 6 | A Albalooshi | Line sizes in the P&IDs are preliminary and this shall be finalized along with Hydraulic calculations during detailed engineering stage of the EPC “The sizes are minimum in the P&IDs”. This document shall be updated after unfreezing the “HOLD” from the P&IDs.