## 082-C-GAD-00002-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Ahmed Bucheeri | To confirm the selection of the 304SS cladding, since feed MSD does not show metallic internal lining
2 | Cloud+ | 1 | MAK | Fill in EX and PN nos.
3 | Cloud+ | 1 | MAK | 082 - REFINERY SOUTH FLARE
4 | Text Box | 1 | MAK | General Comment: All the texts in drawings shall be searchable and in UPPERCASE. Text fonts and styles shall be as per BMPS-A8.
5 | Call-out | 1 | Ahmed Bucheeri | This comment is related to the W.O.L above comment: As per FEED sheet the spec of internal piping is SA 333 and for forgings is SA 105N or SA 350 LF2. To clarify the change from SA 333 to 304SS material for internal piping and from SA 105N to 105 for forgings and SA 403 304L for internal fittings
6 | Callout | 1 | A Albalooshi | Line sizes in the P&IDs are preliminary and this shall be finalized along with Hydraulic calculations during detailed engineering stage of the EPC “The sizes are minimum in the P&IDs”. This document shall be updated after unfreezing the “HOLD” from the P&IDs.
7 | Cloud+ | 1 | MAK | 3
8 | Text Box | 1 | David.Jimenez | Text is not searchable