## 082-G-DAT-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Isamu | This cover page differs from the ones for other pumps in the same transmittal. Please provide uniform cover page
2 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
3 | Text Box | 4 | Isamu | Common comment for all pumps where TTSJV selected plan 74:- Owner has no objection to employ this plan (dual gas seal with N2 buffer gas). But careful consideration shall be given to NPSHA issue because the small amount of N2 that leaks across the process side seal will mix with process liquid causing bubble formation and possible lose of suction due to limited NPSHA as it is the case with this pump. Please discuss the matter in depth with the engineer of successful vendor and his seal supplier before deciding to go to plan 74 in lieu of 53
4 | Text Box | 5 | Isamu | Please comply with FEED DS requirement for witnessed inspection and test. Changing to observed is rejected without Owner prior approval on selected test and selected pump on case by case basis. There is no "Observe" level of inspection in the ITB (BMPS-G-50309) and "witness" must be retained on the data sheet in line with the definition of the ITP. Also Refer to BMPS-B11 / BMPS-G1 / API 610 parag 3.64 and 3.38 for definitions of witness.