## 082-G-DAT-00001-001-RB-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | General Comments: - Use the latest datasheet template that is part of the Homogenization Procedure. - The Equipment List for Unit 082 shall be submitted to Bapco for review.
2 | Cloud+ | 2 | MAK | 082 - REFINERY SOUTH FLARE
3 | Text Box | 2 | A Albalooshi | The information provided for the driver starting method of the pumps is not applicable (Closed/Open – valve (unloaded) start)), It shall be corrected as DOL or VFD starting method as per detail design. Please provide the basis/ philosophy of providing this requirement on the driver starting method. A general note shall be added as follows "Motors shall be designed to suite the driver online starting method as per BMPS-P19 clause 5.4 and BMPS-P18 clause 5.4.". The (Closed/Open – valve (unloaded) start)) shall be moved in the relevant field in the data sheet.
4 | Cloud+ | 2 | MAK | Change on all pages to: X/Y
5 | Callout | 3 | A Albalooshi | Please advise level 3 inspection class basis
6 | Callout | 3 | A Albalooshi | Please provide a documentary proof with calculations that hydraulic fit is not required.
7 | Callout | 4 | A Albalooshi | Cooling water is required as per FEED data sheet.