## 082-G-DAT-00002-001-RB-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | General Comments: - Use the latest datasheet template that is part of the Homogenization Procedure. - The Equipment List for Unit 082 shall be submitted to Bapco for review.
2 | Cloud+ | 2 | MAK | Change on all pages to: X/Y
3 | Cloud+ | 2 | Mahdi Ali | 082 - REFINERY SOUTH FLARE
4 | Text Box | 2 | A Albalooshi | The information provided for the driver starting method of the pumps is not applicable (Closed/Open – valve (unloaded) start)), It shall be corrected as DOL or VFD starting method as per detail design. Please provide the basis/ philosophy of providing this requirement on the driver starting method. A general note shall be added as follows "Motors shall be designed to suite the driver online starting method as per BMPS-P19 clause 5.4 and BMPS-P18 clause 5.4.". The (Closed/Open – valve (unloaded) start)) shall be moved in the relevant field in the data sheet.
5 | Callout | 3 | A Albalooshi | Please provide a documentary proof with calculations that hydraulic fit is not required.
6 | Callout | 3 | A Albalooshi | Please advise level 3 inspection class basis
7 | Text Box | 4 | AliRedha Malalla | -18
8 | Text Box | 4 | AliRedha Malalla | Hazardous service (H2S); piping to be specified instead of tubing. FEED DS to take precedence over BMPS-G9.
9 | Text Box | 7 | AliRedha Malalla | 18. PUMP & M/SEAL OEM SHALL PROVIDE MEASURED STUFFING BOX PRESSURE AND ENSURE THE PRESSURIZED SEAL SYSTEM CAN HANDLE THE STUFFING BOX PRESSURE i.e. HIGHER BY 1.4 BAR.