## 180-A-STS-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | REFINERY SOUTH CONTROL BUILDING
2 | Callout | 1 | Mahdi Ali | THIS DOCUMENT IS A CALCULATION SHEET AND NOT A STUDY. THUS THE DOCUMENT TYPE SHALL BE 'CAL' AND NOT 'STS'. CHANGE ALL THE REFERENCES TO THIS DOCUMENT ACCORDIGNLY. HOWEVER, IF THIS DOCUMENT IS A STUDY THEN THE TITLE SHOULD BE CHANGED ACCORDINGLY.
3 | Text Box | 1 | MAK | Bapco has not received the Unit Equipment List (Item Index) for review. How to cross check the correctness/completeness of equipment numbers within this document?? Equipment List is the master index and shall be issued before issuing this document.
4 | Callout | 2 | David.Jimenez | Please include meaning for notes 1,2 and 3
5 | Cloud+ | 2 | MAK | Include pumps motors: 180M0001A 180M0001B
6 | Text Box | 2 | steven.coyne | Add Note : Criticality Rating Procedure 000-A-PRO-50017-001
7 | Text Box | 2 | MAK | Include all the equipment and drivers in the list