## 371-A-BOD-50001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Julio.Aguilar | This BOD shall be revised and reissued for review after completion and finalization of steam production and consumption balance.
2 | Text Box | 1 | Jeung.Kim | IMPORTANT Note: There are several changes from the FEED basis such as operation basis of the turbines or motors for air compressor, and also operation ratio for existing boiler. Any change from the Contract has to be separately written Owner approved as Deviation/Waiver. Any change without separate written Owner approval will not be valid.
3 | Callout | 5 | Jeung.Kim | Why this is increased from 300Mlb?
4 | Callout | 5 | Julio.Aguilar | FEED Process Design Basis considered 55%. Why this figure now is different. Add note explaining the reasons
5 | Text Box | 6 | Jeung.Kim | Any deviation or change from the FEED or Contract has to be brought to Owner Approval and any change from FEED/Contract in this Design basis will not be effective without Owner deviation approval.
6 | Callout | 6 | Jeung.Kim | Why this is changed from 60 psig?
7 | Cloud+ | 6 | Sameer.Ahmed | 341T3420A as per latest Equipment list
8 | Callout | 6 | Julio.Aguilar | Feed BOD considered two steam turbine driven compressors. Philosophy is to operate with the two turbines and the two motors to be
9 | Callout | 6 | A Albalooshi | One air compress or two ? please confirm.
10 | Callout | 6 | A Albalooshi | Two or Three main cooling water circulation pump steam turbine drivers. Please confirm
11 | Cloud+ | 7 | Julio.Aguilar | Tag number to be updated as per last approved for the project for the unit, 341T3420B
12 | Callout | 7 | Ebrahim.Deyab | Auto start facility to be provided, currently this facility is not equipped as the turbine is called " Special Purpose)
13 | Cloud+ | 8 | Julio.Aguilar | FEED BOD shows different value. Explain basis of this new figure
14 | Callout | 8 | Julio.Aguilar | Review and confirm this new operation philosophy.
15 | Cloud+ | 9 | Sameer.Ahmed | These scenarios need to discussed in details with the owner considering all the factors as it will not be acceptable to run the boilers at very high load (at or near the MCR)
16 | Cloud+ | 10 | Julio.Aguilar | Explain and confirm increasing of 10 % in the MCR
17 | Callout | 12 | Ebrahim.Deyab | During LSDP shutdown, the first two days the Recycle compressor will be in service for cooling purpose consuming about 80 mlb/hr of 550 steam. This should be considered.
18 | Callout | 13 | Julio.Aguilar | TTSJV shall explain the basis for arriving at this value. What capacity utilization for 5/6/7 SRUs and 3/4 TGTU consider for estimating steam production.
19 | Callout | 13 | Julio.Aguilar | TTSJV shall explain the basis for arriving at this value. What capacity utilization for 3/4 H2P consider for estimating steam production.
20 | Cloud+ | 13 | Julio.Aguilar | Explain basis to get this value for the steam boilers.
21 | Cloud+ | 13 | Sameer.Ahmed | Is this figure considering 2 or 3 Desals running?
22 | Call-out | 20 | Hasan Al Noaimi | HUB south
23 | Call-out | 20 | Hasan Al Noaimi | HUB North
24 | Callout | 21 | Sameer.Ahmed | Some of steam turbines' steam consumption have increased as compared with the FEED value. This may be caused by vendor's data for steam turbines with lower efficiency than what is stated in the below table. Turbine vendors should at least comply with the below efficiency to avoid higher steam consumption for the same power shaft.
25 | Cloud+ | 27 | Sameer.Ahmed | Unit 370
26 | Callout | 28 | Julio.Aguilar | This will be a new operation philosophy for the new desal plants and it was not considered during FEED. This alternative option need to be discussed in separate meeting with the team and confirmed by vendor
27 | Callout | 28 | Sameer.Ahmed | If the intention is to have the desalination units to operate on both 550# and 60# steam, this may be not feasible due to big differences of the steam characteristics of these steam
28 | Cloud+ | 30 | Sameer.Ahmed | CWT
29 | Call-out | 30 | Hasan Al Noaimi | HUB South
30 | Cloud+ | 34 | Khalid | Special purpose turbines should NOT be in standby mode
31 | Cloud+ | 36 | Khalid | Too high, sizing finfan coolers 50X bigger than normal requirement!!