## 371-A-BOD-50002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mahdi Ali | DELETE
2 | Callout | 1 | Mahdi Ali | FOLLOW THE HOMOGENIZATION PROCEDURE FOR THE UNIT DESCRIPTIONS. UNIT 371 DESCRIPTION IS 'STEAM DISTRIBUTION'
3 | Text Box | 11 | David.Jimenez | describes
4 | Callout | 11 | Mahdi Ali | AVOID THE USE OF THE WORD 'NEW'
5 | Cloud+ | 11 | MAK | Should this be changed to 371DS0001A/B?
6 | Text Box | 11 | David.Jimenez | have
7 | Callout | 11 | David.Jimenez | are
8 | Call-out | 12 | Edgardo | Please change "condensate" to "condensed"
9 | Callout | 13 | David.Jimenez | order and
10 | Callout | 13 | David.Jimenez | order and
11 | Text Box | 14 | David.Jimenez | order and