## 371-A-PFD-50001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Group | 1 | Mahdi Ali | MODIFICATIONS TO BAPCO EXISTING DRAWINGS SHALL BE CLOUDED AS PER BMPS-A8 SECTION 5.4.1 ITEM 7
2 | Callout | 1 | Julio.Aguilar | Add stream number
3 | Call-out | 1 | MAK | General Comments: Enter full drawing number in all OPC's, e.g. 371-A-PFD-50001-002
4 | Cloud+ | 1 | Julio.Aguilar | Line destination to be to 20 psig header.