## 371-A-STS-50001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | Bapco has not received the Unit Equipment List (Item Index) for review. How to cross check the correctness/completeness of equipment numbers within this document?? Equipment List is the master index and shall be issued before issuing this document.
2 | Callout | 1 | Mahdi Ali | THIS DOCUMENT IS A CALCULATION SHEET AND NOT A STUDY. THUS THE DOCUMENT TYPE SHALL BE 'CAL' AND NOT 'STS'. CHANGE ALL THE REFERENCES TO THIS DOCUMENT ACCORDIGNLY. HOWEVER, IF THIS DOCUMENT IS A STUDY THEN THE TITLE SHOULD BE CHANGED ACCORDINGLY.
3 | Call-out | 2 | Ebrahim | Bases of the given values need to be defined or shall be referenced to a document
4 | Call-out | 2 | Ebrahim | Criticality Rating to be defined
5 | Typewritten Text | 2 | steven.coyne | Add reference to 000-A-PRO-50017-001 Criticality Rating Procedure
6 | Call-out | 2 | Ebrahim | Do not use short form of description. Typical
7 | Text Box | 2 | MAK | General Comment: Equipment List for Unit 371 was not issued for review. However, this list shall perfectly match Unit 371 - Equipment List (Item Index). All Units equipment shall be included for Criticality Rating Evaluation.
8 | Callout | 2 | David.Jimenez | Notes 1, 2 and 3 have not been explained
9 | Call-out | 2 | Ebrahim | Motors are not listed?!