## 371-C-DAT-55001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | General Comment: This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used for all Unfired Pressure Vessels.
2 | Text Box | 1 | seongjin.lee | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
3 | Callout | 2 | Saeed Taher | B7 or B7M as to be consistent with removable internal piping material
4 | Cloud+ | 2 | Julio.Aguilar | Review this figures as per BMPS-A3, 14.7 psig@ 378 F
5 | Cloud+ | 3 | Julio.Aguilar | Remove, this is for horizontal vessels
6 | Callout | 3 | Sang.Hwang | Non-applicable standard shall be deleted from this data sheet. This typical comment for all data sheet.
7 | Callout | 3 | Julio.Aguilar | Add:, BMPS-SF-C-53
8 | Cloud+ | 3 | Julio.Aguilar | It shall be responsibility of the manufacturer to complete the datasheet where the information is not filled.
9 | Text Box | 3 | JaiMun.Oh | Painting shall be performed as per BMPS-B5.
10 | Text Box | 4 | Julio.Aguilar | Confirm if vortex breaker is required