## 371-E-DAT-50002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Cloud+ | 1 | MAK | Change on all pages to: STEAM DISTRIBUTION
3 | Call-out | 2 | Mohamed Aldoseri | Note 10 is not related to electrical motor data details
4 | Callout | 2 | David.Jimenez | pleases use readable font size
5 | Call-out | 2 | Mohamed Aldoseri | RPM is required
6 | Callout | 3 | A Albalooshi | Please advise why10% over design is not required
7 | Text Box | 3 | Mohamed Aldoseri | No. of drivers related to 371E0001 shall be mentioned in this Data sheet.
8 | Callout | 3 | A Albalooshi | delete
9 | Text Box | 3 | Mohamed Aldoseri | 22) Driver data sheet shall be submitted for owner review.