## 371-G-DAT-50001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Call-out | 2 | Mohamed Aldoseri | Refer to note 3.
3 | Call-out | 2 | Mohamed Aldoseri | Tempreture class to be provided
4 | Call-out | 2 | Mohamed Aldoseri | Re-write, FREQUENCY
5 | Callout | 2 | Mahdi Ali | INCORRECT UNIT DESCRIPTION
6 | Call-out | 3 | Edgardo | Please confirm the availability of oil mist at the area where this pump will be installed; as noted in PFD of Unit 371, there are only four pumps in this Unit
7 | Callout | 5 | Isamu | See next page
8 | Text Box | 7 | Isamu | This is non API pump so note 18 can not be applied here. Please seek practical solution and meet with Kuniyama