## 371-G-DAT-55001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Callout | 2 | Ebrahim.Deyab | Pumps capacity to be finalized after utility balance completion and approved
3 | Callout | 2 | Julio.Aguilar | Figures shall be updated when the final hydraulic calculation is finalized.
4 | Text Box | 2 | hyunjin.paeng | To be specified
5 | Callout | 3 | hyunjin.paeng | inspection level to be specified
6 | Callout | 7 | Julio.Aguilar | Add note as: “It shall be responsibility of manufacturer to complete the datasheet when the information is not available”
7 | Text Box | 7 | hyunjin.paeng | API 610 definitions of “ WITNESSED”, OBSERVED” and “NON-WITNESSED” shall be interpreted respectively as “HOLD” “WITNESS”, “REVIEW” as per the prevailing definition in the ITP which is integral part of Material Requisition(MR).