## 371-S-DAT-55001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | STEAM DISTRIBUTION
2 | Callout | 1 | Julio.Aguilar | Confirm unit name as per last approved by the project
3 | Text Box | 1 | seongjin.lee | he document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
4 | Text Box | 1 | MAK | General Comment: The page headers of this datasheet shall be consistent with the other datasheets that are part of the Homogenization Procedure.
5 | Text Box | 1 | Julio.Aguilar | Description name is not consistency with the name in the coversheet. review and confirm
6 | Cloud+ | 1 | MAK | Use the correct equipment no. 371OMG0001
7 | Cloud+ | 2 | MAK | 371 - STEAM DISTRIBUTION
8 | Callout | 2 | Julio.Aguilar | Description name is not consistency with the name in the coversheet. Review and confirm
9 | Text Box | 3 | hyunjin.paeng | To be marked
10 | Text Box | 3 | Aamer.Hubail | BST piping shall include flexible hose attached to a lance and proper valving to use air operated pump ref BMPS G8 - 7.1.2.6
11 | Text Box | 3 | Aamer.Hubail | 10 micron inlet air filter with auto drain routed to outside of OMG cabinet ref to BMPS G8 – 6.1.3.1
12 | Text Box | 4 | hyunjin.paeng | To be marked
13 | Text Box | 4 | hyunjin.paeng | To be marked
14 | Text Box | 4 | hyunjin.paeng | Oil mist return connection to be specified