## 372-A-MSD-54001-011-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | Sameer.Ahmed | Do not use FEED reference drawings number, use the numbers assigned as per the detailed engineering phase.
2 | Text Box | 1 | Sameer.Ahmed | General comment: The MSD shall be revised based on the latest revised PFD to reflect all changes