## 372-A-PFD-54001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | NTS
2 | Callout | 1 | Julio.Aguilar | Dedicated secondary line to flare to be reinstated. This utility water line is used in the flare recovery package vessel V8203
3 | Call-out | 1 | Ali Abbas | add arrow direction. General for all sheets
4 | Callout | 1 | Syed Ahmed | keep this valve black as per BMPS as normal NFF
5 | Text Box | 1 | MAK | A1
6 | Text Box | 1 | MAK | General Comment: Follow the equipment nos. that have been sent officially through Project Mailbox.
7 | Callout | 1 | Syed Ahmed | keep this valve black as normal NFF
8 | Text Box | 1 | alexis.martinez | GENERAL: "The PFD should represent a normal operating case for the unit. The data included in the equipment data blocks should be consistent with the PFD heat and material balance. Therefore, for pump/compressor data (capacity, suction pressure, and discharge pressure) and exchanger/furnace duties, operating case data should be used. A note clarifying this fact should be included on the PFDs." BMPS-A8
9 | Call-out | 1 | MAK | 17
10 | Text Box | 1 | MAK | General Comment: The equipment data shall be placed in alignment with the location of the equipment as possible.
11 | Callout | 1 | Syed Ahmed | NFF
12 | Cloud+ | 1 | Julio.Aguilar | Existing PFD numbers to be indicated, if the existing PFD is not available includes a note referring existing PID number for details
13 | Text Box | 1 | MAK | Use the latest PFD border and off-page connectors that are part of the Homogenization Procedure. SOC shall coordinate with TTSJV.
14 | Text Box | 1 | Julio.Aguilar | Pumps 372P3730C and 372P3731C to be reinstated in the PFD as they are feed pumps to Demin plant and make-up to Cooling water towers respectively. They are critical pumps recommended to be included in the FEED Hazop and for critical pumps the philosophy mentioned is N+2; 1 pump in operation, one pump in stand-by and one pump in spare. See Process basis of design for sparing philosophy details.
15 | Callout | 1 | Julio.Aguilar | General Comment for all PFDs: Reference PFD number presentation to be consistent across BMP.
16 | Cloud+ | 1 | Julio.Aguilar | Existing PFD numbers to be indicated, if the existing PFD is not available includes a note referring existing PID number for details
17 | Callout | 1 | alexis.martinez | In Note 3, delete the word "both"