## 372-A-PFD-54001-004-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | A1
2 | Text Box | 1 | MAK | NTS
3 | Call-out | 1 | MAK | 17
4 | Text Box | 1 | MAK | Use the latest PFD border and off-page connectors that are part of the Homogenization Procedure. SOC shall coordinate with TTSJV.
5 | Cloud+ | 1 | Julio.Aguilar | Update pump 372P3740C in the description
6 | Cloud+ | 1 | Julio.Aguilar | Existing PFD numbers to be indicated, if the existing PFDs are not available includes a note referring existing PID number for details
7 | Call-out | 1 | MAK | Change to 372V0013/0023