## 372-A-PFD-54001-010-RB-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Julio.Aguilar | Ensure use the last approved equipment numbering for the new unit 370.
2 | Text Box | 1 | BD Mori | The PFDs of unit 372 and newly created unit 370 shall be segregated and also stream data shall be segregated . After segregation, new PFD numbers shall be assigned.
3 | Text Box | 1 | Julio.Aguilar | Drafting shall be as per BMPS-A8. Show Main, Secondary and Minor lines properly.
4 | Callout | 1 | Ebrahim.Deyab | Remove "both"
5 | Cloud+ | 1 | Julio.Aguilar | PFD will belong to unit 370