## 372-A-PFD-54001-011-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | A1
2 | Cloud+ | 1 | Julio.Aguilar | Remove
3 | Text Box | 1 | MAK | NTS
4 | Text Box | 1 | MAK | General Comment: Follow the equipment nos. that have been sent officially through Project Mailbox.
5 | Text Box | 1 | MAK | Use the latest PFD border and off-page connectors that are part of the Homogenization Procedure. SOC shall coordinate with TTSJV.
6 | Callout | 1 | Julio.Aguilar | Include the stream line and PFD number coming from unit 371, stream 97. Add stream description: "60 PSIG STEAM FROM 60 STEAM MAIN AND SECONDARY HEADERS"
7 | Call-out | 1 | MAK | 17
8 | Text Box | 1 | Julio.Aguilar | Pumps 372P3746C to be reinstated in the PFD as they are feed pumps to the new HP Boilers. They are critical pumps recommended to be included in the FEED Hazop and for critical pumps the philosophy mentioned is N+2; 1 pump in operation, one pump in stand-by and one pump in spare. See Process basis of design for sparing philosophy details.
9 | Cloud+ | 1 | Julio.Aguilar | Figures for capacity and differential pressure are different to the FEED PFD. Advise the reasons for this change?