## 372-A-PFD-54002-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Julio.Aguilar | Utility water to be provided to Flare as secondary line as per comment on sheet one | To be Incorporated. | Y
2 | Callout | 1 | Khalid | Secondary header - refer to ITB doc (BRB-228972 sh 1/17 rev0) | To be Incorporated. | Y
3 | Cloud+ | 1 | Sameer.Ahmed | 1N2 Plant is 083 | To be Incorporated. | Y
4 | Callout | 1 | Salman Jaffer | Rename to (REFINERY SOUTH FLARE) | To be Incorporated. | Y
5 | Cloud+ | 1 | Sameer.Ahmed | Change to CWT | To be Incorporated. | Y
6 | Callout | 1 | Julio.Aguilar | EVAPORATED | To be Incorporated. | Y
7 | Callout | 1 | Salman Jaffer | Please include 1HRU (UNIT023) | To be Incorporated. | Y
8 | Call-out | 1 | Sameer.Ahmed | 3 | To be Incorporated. | Y